## Sheet1
LOAN APPLICATION FORM.
1 | Project Cost field should be disabled in application form.
2 | Replace name of Unit into telephone number in guranter details.
3 | Amount of gauranty should be equal to maximum loan amount. And should be disabled.
4 | Superannuation date should not be compulsory.
5 | Document Required field need to be recreated.
FIELD OFFICER VERIFICATION:

## HPBC Closure Plan
Milestones | Task ID | Descriptions | Resources | Estimation Efforts(in Days) | Start Date | DeadLine | Status Remark
Application Audit | HBC-1001 | Set up application for Test Environment. | Himanshu | 1 | 26-08-2016 | 26-08-2016 | Done
| HBC-1002 | Security Audit of HPBC Application. | Himanshu, Mahesh | 30 | 29-08-2016 | 30-09-2016
Code Fix | HBC-1003 | Run a cron to apply interest on on Live accounts upto 30-09-2016. | Himanshu | 5 | 28-08-2016 | 31-08-2016
| HBC-1004 | User Interface to correct demographic Loanee Data | Himanshu | 4 | 2016-01-09 | 2016-04-09
| HBC-1005 | Test SMS cron functionality on Live Server | Himanshu | 3 | 2016-05-09 | 2016-07-09
Data Fix | HBC-1006 | Manual Interest Application on Live Loan accounts upto 30-06-2016 | Himanshu | 24 | 2016-08-09 | 2016-01-10
| HBC-1007 | Apply interest of 30-09-2016 through running interest script | Himanshu | 1 | 2016-03-10 | 2016-03-10
Reports Fix | HBC-1008 | Check Loan Reports and data on Reports. | Himanshu | 2 | 2016-05-10 | 2016-06-10
| HBC-1009 | Education Loan System Check | Himanshu | 3 | 2016-07-10 | 2016-09-10
Final Touch | HBC-1010 | Other Modules Status check | Himanshu | 2 | 2016-10-10 | 2016-11-10
| HBC-1011 | Upload latest content on website frontend. | Himanshu | 1 | 2016-12-10 | 2016-12-10
| HBC-1012 | User and Application Final Touch (Testing) | Himanshu | 2 | 13-10-2016 | 14-10-2016
Go Live | HBC-1013 | HPBC Application GO Live | Himanshu | 1 | 15-10-2016 | 15-10-2016
1 | Check up online statement for public users.

## HBC-1003
Requirements Gathering
1 | Filter Live Loan accounts (Excluding LD Only Cases). |  |  |  |  | Total | 3612
2 | Interest Rate, Last Int Cal Date, Principal amount on LICD, O_principal, List of Repayments with in Quarter. |  |  |  |  | Closed | 1643
3 | Drupal 6 Autocron functionality should be implemented. |  |  |  |  | Live | 1969
4 | Cron run time is 12:00 AM of last date of every quarter.
Wireframe Analysis
1 | Develop a test autocron in D6, that will take input variable from DB and write result in DB after some manupulation on input variable.
Design Structure Analysis
Read Inputs
Write Interest Results
Write Interest results
Read Json input var
Task Lists
1 | Include date in .txt filename ( int-2016-09-30)
3 | Setup Auto cron rule for running int cal cron.
4 | Only one .txt file of existing quarter should be there.
5 | once written to DB, can not write again.
6 | One SMS shouldbe fired on interest accrud
7 | Last int date of selected loan acc should be older than quarter end date. (implementation required at cron level)
Important steps for Outstanding Principal Data Flow.
1 | START PROCESS : update o_principal with last quarter start time time.
2 | MIDDLE PROCESS : upto date with end of quarter o_principal.
3 | END PROCESS : Calculate repayments and deduct from o_principal on the basis of current date.
HBCFDC LOAN DATABASE
INPUT LIVE LOAN ACCOUNTS IN JSON ARRAY FORMAT
PROCESS TO CALCULATE INTEREST OF LIVE LOAN ACCOUNTS
OUTPUT INTEREST OF LOAN ACCOUNTS IN JSON FORMAT
WRITE PROTECTED TEXT FILE TO STORE RETURN RESULT FOR FUTURE PURPOSE.
LOAN_ID{
ROI;
LICD;
PLICD;
OP;
......
}

## Sheet2
Interest Quarter Analysis
Quarter End Date | Total Loan Ac | Status | Reference File
31-03-2014 | 0 | NA | NA
30-06-2014 | 217
30-09-2014 | 217
31-12-2014 | 217
31-03-2015 | 219
30-06-2015 | 221
30-09-2015 | 687
31-12-2015 | 1153
31-03-2016 | 1580

## Other Modules
Sr No. | Module Name | Status | Remarks
1 | Court Case Management | OKAY
2 | Establishment Management
4 | Assets Management | OKAY
5 | RTI Management | CAN NOT CHECK
6 | Dispatch Management | PARTIALLY OKAY
7 | EMI and Interest Calculator | OKAY
8 | HelpDesk
9 | Document Management
10 | ALR Recovery
11 | Budget Management
12 | Web Portal Management
13 | Lokmitra Management
1 | Court Case Management | OKAY
2 | Assets Management | OKAY
3 | RTI Management | FIELDS ARE DISABLED ON RTI GRIEVANCE FORM
4 | Dispatch Management | INBOUND MAILS FIELDS ARE DISABLED.
5 | EMI and Interest Calculator | OKAY
6 | HelpDesk | OKAY | SEEMS TO BE INCOMPELTE
7 | Document Management | DOWNLOAD LINK HAVE SOME ISSUE WITH ADMIN LOGIN
8 | ALR Recovery | WILL STUDY AT CODE LEVEL.
9 | Budget Management | All okay
10 | Web Portal Management | OKAY
11 | Lokmitra Management | ALL OKAY
12 | Establishment Management | LIST OF REGISTRATION IS NOT WORKING
LEFT MODULES.
1 | FINANCE MANAGEMENT
2 | AUDIT MANAGEMENT
3 | LOAN ADVANCE MANAGEMENT
4 | CLAIM AND BILLS MANAGEMENT